## Read me
Portfolio workbook · Full
A record of every program and project in one portfolio, kept by hand. Six tabs: Read me, Portfolio, Register, Funding, Steering and Checks.
Filling it in
1 | On Portfolio, type the portfolio's name, director, manager and status. If a steering group meets, pick how often, and add a First review date if it hasn't met yet.
2 | On Register, add a row for every program and every project, with Sits under, Status and Owner. On projects, pick an Approach in the last column, after Check.
3 | Type Planned finish, Latest forecast and Forecast spend, and Budget on programs and on projects directly under Portfolio. On Funding, type the envelope, its currency and where it came from.
4 | Read Health and Check on Register, and the Checks tab for every result. Write a Variance note on every Amber or Red row, ending with your name.
5 | After each steering meeting, add it under Meetings on Steering. Then log its decisions, each with one accountable person and who recorded it, and any actions with an owner and a due date.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
NAMES
Type each person's name the same way every time, with a role in brackets if you like: Priya (CTO). Names are matched exactly as typed, so Priya and Priya (CTO) count as two people.
READING THE MARKS
■ Red | Late, or over budget, by more than your limit. The limits are on the Checks tab, and you can change them.
◧ Amber | Late, or over budget, within your limit.
□ On track | A date or a budget was read, and nothing is late or over.
Not read | Nothing to judge from yet. A project with a Planned finish and no Latest forecast reads Not read; if the date hasn't moved, type it again as the forecast. A Sprint project always reads Not read.
Not counted | Proposed, Completed or Terminated. Left out of every count.
△ | A check found something, and the words say what. Filter the Check column on △ to list them all.
○ Clear | The check found nothing.
HOW HEALTH IS WORKED OUT
Dates: a project is Red once its Planned finish has passed while it's still Active or Paused. Otherwise a Latest forecast past the plan by more than your limit is Red, and a smaller slip is Amber.
Money: spend over Budget by more than your limit is Red, and a smaller overrun is Amber. A program's spend is its projects' Forecast spend added up.
Health is the worse of the two. A program with no Latest forecast uses the latest among its projects. Its colour never hides theirs: Projects inside counts its Red and Amber projects beside it.
GREY COLUMNS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
Owner's current rows counts the Active and Paused rows that carry each owner's name, so you can see who's spread thin. It sets no limit.
THE STARTER WORKBOOK
A small team that wants fewer tabs can use the Starter workbook. Its Register columns A to L match this one, so rows paste across.

## Portfolio
Portfolio
One portfolio per workbook. Type in the white cells; the grey ones are worked out.
THE PORTFOLIO
PORTFOLIO NAME |  | What you call the work this workbook covers. Required.
DIRECTOR |  | The person accountable for the portfolio's direction and benefits. A name, with a role in brackets if you like. Required.
MANAGER |  | The person who runs it day to day and keeps the register. Can be the director. Required.
STATUS |  | Where the portfolio is in its life. Blank counts as Active. Reviews are checked only while it's Active.
REVIEW CADENCE |  | How often the steering group reviews the portfolio. Leave blank if there isn't one.
FIRST REVIEW |  | The date of the first review, while no meeting is logged on Steering. Optional.
LAST REVIEW |  | Worked out: the latest meeting date on Steering.
NEXT REVIEW |  | Worked out: Last review plus the cadence, or First review until a meeting is logged.
PEOPLE CHECK |  | Shows △ when the director or the manager isn't named.
REVIEW CHECK |  | Shows △ when the next review has passed, or a cadence is set with no review date.
COUNTS BY HEALTH |  | Programs and projects directly under Portfolio, one count each. A program's own projects are counted beside it on Register.
■ Red
◧ Amber
□ On track
Not read
CURRENT ROWS OUTSIDE THE PORTFOLIO |  | Active or Paused rows with Sits under set to Outside the portfolio. Left out of the counts above.
CHECKS |  | Every result is on the Checks tab.
OBJECTIVES
Objective | Owner | Measure and target | Target date | Linked rows

## Register
Register
Name | Level | Sits under | Status | Owner | Sponsor | Objective | Planned finish | Latest forecast | Forecast spend | Budget | Variance note | Health | Projects inside | Owner's current rows | Check | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Approach | Helper, worked out | Helper, worked out | Helper, worked out
Portfolio
Outside the portfolio
Formulas:
Helper, worked out = IF(OR([Helper, worked out]=0,[Planned finish]="",[Approach]="Sprint"),0,IF(AND([Level]="Project",[Planned finish]<TODAY()),3,IF([Helper, worked out]="",0,IF([Helper, worked out]<=[Planned finish],1,IF(NETWORKDAYS([Planned finish],[Helper, worked out])-1>IF([Level]="Program",Checks!$B7,Checks!$B6),3,2)))))
Note on M5: Worked out. Don't type here.
Note on N5: Worked out. Don't type here.
Note on O5: Worked out. Don't type here.

## Funding
Funding
ENVELOPE
ENVELOPE |  | The total the portfolio may spend. Optional; leave it blank and the envelope check doesn't run.
CURRENCY |  | The currency of every figure in this workbook. Pick one, or type another code.
SOURCE |  | Where the figure came from, such as a plan or a board decision, with its date.
SET BY |  | Who set the figure, or last changed it.
BUDGETS GIVEN OUT |  | Every Budget on a row directly under Portfolio, Proposed rows left out. When a row closes, lower its Budget to what was spent.
LEFT IN THE ENVELOPE |  | The envelope minus budgets given out. Negative means over.
FORECAST SPEND, ALL PROJECTS |  | Forecast spend added up across this portfolio's projects, Proposed left out.
PROJECTS WITH NO FORECAST SPEND |  | Projects in that total with Forecast spend blank. While there are any, the figure above reads low.
ENVELOPE CHECK |  | Shows △ when budgets given out pass the envelope.
BUDGETS, WORKED OUT FROM THE REGISTER
Name | Budget | Level | Status | Forecast spend | Against budget
Note on E17: A program's figure is its projects' Forecast spend added up.
Note on F17: Forecast spend minus Budget. Negative means under.

## Steering
Steering log
Decisions |  |  |  |  | Meetings |  | Actions
Date | Decision | Accountable | Check | Recorded by | Meeting date | Attended | Meeting date | Action | Owner | Due

## Checks
Checks
LIMITS FOR RED
DAYS LATE BEFORE RED, PROJECTS |  | Working days a project may run past its Planned finish before it reads Red. Starts at 5; change it to suit.
DAYS LATE BEFORE RED, PROGRAMS |  | Working days a program may run past its Planned finish before it reads Red. Starts at 10.
OVER BUDGET BEFORE RED |  | How far spend may run over Budget before a row reads Red. A smaller overrun reads Amber. Starts at 10%.
ALL CHECKS
Check | Result | Where to look
A row with no owner |  | Register, Check column
A program with no sponsor |  | Register, Check column
Sits under, or a current row outside the portfolio |  | Register, Check column
Director or manager not named |  | Portfolio, People check
Budgets over the envelope |  | Funding, Envelope check
Budget on a row not directly under Portfolio |  | Register, Check column
Review overdue, or no review date |  | Portfolio, Review check
An objective with no owner |  | Portfolio, Objectives
An Amber or Red row with no variance note |  | Register, Check column
A decision without one accountable person |  | Steering, Decisions
A decision not recorded by the director |  | Steering, Decisions
A name used twice |  | Register, Check column